## Sheet1
Sl.No | Main Pages | Sub Pages | Design Mockup URLs | Design Status / Comments | Duplications
1 | Landing Page |  | http://mockup.blazedream.in/Why_Compare/Landing_03/ | Completed
2 | Home |  | http://mockup.blazedream.in/Why_Compare/Home_03/ | Minor Tweaks
3 | Promotions |  | http://mockup.blazedream.in/Why_Compare/Feb_19/Promotions/ | Minor Tweaks
4 | Mobile - Device | Questions1 |  | Awaiting client feedback
5 |  | list view |  | Awaiting client feedback
6 |  | Casecade view |  | Awaiting client feedback
7 |  | Comparision view |  | Pending
8 |  | Detail page | http://mockup.blazedream.in/Why_Compare/Phone_Detail/ | Awaiting client feedback
9 | Mobile - Device + Services | Questions1 |  | Awaiting client feedback
10 |  | Questions2 |  | Awaiting client feedback
11 |  | list view |  | Awaiting client feedback
12 |  | Casecade view |  | Awaiting client feedback
13 |  | Comparision view |  | Pending
14 |  | Detail page |  | Awaiting client feedback
15 | Mobile - Service Only | Questions1 |  | Awaiting client feedback
16 |  | list view (Prepared) |  | Awaiting client feedback
17 |  | list view (No Contract) |  | Awaiting client feedback
18 |  | Phone Option Light Box |  | Awaiting client feedback
19 |  | Casecade view |  | Awaiting client feedback
20 |  | Comparision view |  | Pending | Duplicate
21 |  | Detail page |  | Awaiting client feedback
22 | Tablet - Device | Questions1 |  | I have to review the design
23 |  | list view |  | I have to review the design
24 |  | Casecade view |  | I have to review the design
25 |  | Comparision view |  | I have to review the design
26 |  | Detail page |  | I have to review the design
27 | Tablet - Device + Services | Questions1 |  | I have to review the design
28 |  | Questions2 |  | I have to review the design
29 |  | list view |  | I have to review the design
30 |  | Casecade view |  | I have to review the design
31 |  | Comparision view |  | Pending | Duplicate
32 |  | Detail page |  | I have to review the design
33 | Tablet - Service Only | Questions1 |  | I have to review the design
34 |  | list view (Prepared) |  | I have to review the design
35 |  | list view (No Contract) |  | I have to review the design
36 |  | Phone Option Light Box |  | I have to review the design
37 |  | Casecade view |  | I have to review the design
38 |  | Comparision view |  | Pending | Duplicate
39 |  | Detail page |  | I have to review the design
40 | Mobile Boardband - Service only | Questions1 | http://mockup.blazedream.in/Why_Compare/Feb_27/Mobile_Broadband/Question_01/ | Minor Tweaks
41 |  | Questions 2 | http://mockup.blazedream.in/Why_Compare/Feb_27/Mobile_Broadband/Question_02/ | Minor Tweaks
42 |  | list view | http://mockup.blazedream.in/Why_Compare/Feb_27/Mobile_Broadband/Result_list/ | Minor Tweaks
43 |  | Casecade view | http://mockup.blazedream.in/Why_Compare/Feb_27/Mobile_Broadband/Result_grid/ | Minor Tweaks
44 |  | Comparision view |  | Pending | Duplicate
45 |  | Detail page | http://mockup.blazedream.in/Why_Compare/Feb_27/Mobile_Broadband/Details/ | Minor Tweaks
46 | HomePhones - Service only | Questions1 | http://mockup.blazedream.in/Why_Compare/Feb_27/Landline/Questions/ | Minor Tweaks
47 |  | list view | http://mockup.blazedream.in/Why_Compare/Feb_27/Landline/Landline_list/ | Minor Tweaks
48 |  | Casecade view | http://mockup.blazedream.in/Why_Compare/Feb_27/Landline/Landline_grid/ | Minor Tweaks
49 |  | Comparision view |  | Pending | Duplicate
50 |  | Detail page | http://mockup.blazedream.in/Why_Compare/Feb_27/Landline/Details/ | Minor Tweaks
51 | Boardband - Service only | Questions1 | http://mockup.blazedream.in/Why_Compare/Feb_24/Question_01/ | Minor Tweaks
52 |  | Questions2 | http://mockup.blazedream.in/Why_Compare/Feb_24/Question_02/ | Minor Tweaks
53 |  | list view | http://mockup.blazedream.in/Why_Compare/Feb_24/Result_list/ | Minor Tweaks
54 |  | Casecade view | http://mockup.blazedream.in/Why_Compare/Feb_24/Result_grid/ | Minor Tweaks
55 |  | Comparision view |  | Pending | Duplicate
56 |  | Detail page | http://mockup.blazedream.in/Why_Compare/Feb_24/NB_Details/ | Minor Tweaks
57 | PayTV - Service Only | Question1 | http://mockup.blazedream.in/Why_Compare/Feb_23/Question_01/ | Minor Tweaks
58 |  | Question pop up | http://mockup.blazedream.in/Why_Compare/Feb_23/Question_popup/ | Minor Tweaks
59 |  | Question2 | http://mockup.blazedream.in/Why_Compare/Feb_23/Question_02/ | Minor Tweaks
60 |  | Question3 | http://mockup.blazedream.in/Why_Compare/Feb_23/Question_03/ | Minor Tweaks
61 |  | List View | http://mockup.blazedream.in/Why_Compare/Feb_25/Pay%20tv/Result_list/ | Minor Tweaks
62 |  | List View More Edit Option pop up | http://mockup.blazedream.in/Why_Compare/Feb_23/Result_list_popup/ | Minor Tweaks
63 |  | Grid View | http://mockup.blazedream.in/Why_Compare/Feb_23/Result_grid/ | Minor Tweaks
64 |  | Comparision |  | Pending | Duplicate
65 |  | Tv Detail Page | http://mockup.blazedream.in/Why_Compare/Feb_25/Pay%20tv/Pay_tv_details/ | Minor Tweaks
66 | HomePhones + BroadBand | Question1 | http://mockup.blazedream.in/Why_Compare/Feb_25/Landline_broadband/Questions_01/ | Minor Tweaks
67 |  | Question2 | http://mockup.blazedream.in/Why_Compare/Feb_25/Landline_broadband/Questions_02/ | Minor Tweaks
68 |  | Question3 | http://mockup.blazedream.in/Why_Compare/Feb_25/Landline_broadband/Questions_03/ | Minor Tweaks
69 |  | Question4 | http://mockup.blazedream.in/Why_Compare/Feb_25/Landline_broadband/Questions_02/ | Minor Tweaks
70 |  | List View | http://mockup.blazedream.in/Why_Compare/Feb_25/Landline_broadband/Landline_Broadband_list/ | Minor Tweaks
71 |  | Grid View | http://mockup.blazedream.in/Why_Compare/Feb_25/Landline_broadband/Landline_Broadband_grid/ | Minor Tweaks
72 |  | Comparision |  | Pending | Duplicate
73 |  | Detail Page |  | Minor Tweaks
74 | Pay TV + Broadband + Landline | Question1 | http://mockup.blazedream.in/Why_Compare/Feb_27/Homephone_Broadband_Landline/Question_01/ | Minor Tweaks
75 |  | Question2 | http://mockup.blazedream.in/Why_Compare/Feb_27/Homephone_Broadband_Landline/Question_02/ | Minor Tweaks
76 |  | Question3 | http://mockup.blazedream.in/Why_Compare/Feb_27/Homephone_Broadband_Landline/Question_03/ | Minor Tweaks
77 |  | List View | http://mockup.blazedream.in/Why_Compare/Feb_27/Homephone_Broadband_Landline/Result_list/ | Minor Tweaks
78 |  | Grid View | http://mockup.blazedream.in/Why_Compare/Feb_27/Homephone_Broadband_Landline/Result_grid/ | Minor Tweaks
79 |  | Detail Page | http://mockup.blazedream.in/Why_Compare/Feb_27/Homephone_Broadband_Landline/Details/ | Minor Tweaks
80 | Shortlisted | Shortlisted Produsts |  | Minor Tweaks
81 | MyServices | Myservice Products |  | Minor Tweaks
82 | Net Promoter Score (Feedback) |  |  | Pending
83 | News | Latest News list | http://mockup.blazedream.in/Why_Compare/News_Listing/ | Minor Tweaks
84 |  | News Detail Page | http://mockup.blazedream.in/Why_Compare/News_Detail/ | Minor Tweaks
85 | Invites | Add Invites | http://mockup.blazedream.in/Why_Compare/Feb_18/Add_Invites/ | Minor Tweaks
86 |  | Personal Invites | http://mockup.blazedream.in/Why_Compare/Feb_19/My_Invites/ | Minor Tweaks
87 |  | Social Invites | http://mockup.blazedream.in/Why_Compare/Feb_19/Social_Invites/ | Minor Tweaks
88 |  | Package Down Grade Page |  | Pending
89 | My Profile |  |  | Pending
90 | Providers |  |  | Pending
91 | Account management ( Plans Options ) |  | http://mockup.blazedream.in/Why_Compare/Feb_19/Select_Plan/ | Minor Tweaks
92 | Plan Detail Page |  | http://mockup.blazedream.in/Why_Compare/Feb_19/Plan%20Details/ | Minor Tweaks
93 | Quick LInks |  |  | Pending
94 | Budget |  |  | Pending
95 | Rewards |  | http://mockup.blazedream.in/Why_Compare/Rewards/ | Minor Tweaks
96 | Trade Inn |  |  | Scope Creep
97 | Escalate Issues |  |  | Pending
98 | Reviews |  |  | Pending
99 | Review Details |  |  | Pending
100 | Fetch TV |  |  | Pending
101 | FOXTEL |  |  | Pending
102 | T-Box |  |  | Pending
103 | Vendors / Provider section |  |  | Pending
104 | Vendor home (Statistics) |  |  | Pending
105 | Vendor Plans |  |  | Pending
106 | Vendor plan detail page |  |  | Pending
107 | Vendor Add New Plan |  |  | Pending
108 | Vendor Plan Review |  |  | Pending
109 | Vendor Edit Plan |  |  | Pending
110 | Vendor Devices |  |  | Pending
111 | Vendor device detail page |  |  | Pending
112 | Vendor Device Review |  |  | Pending
113 | Vendor Add New Device |  |  | Pending
114 | Vendor Edit Device |  |  | Pending
115 | Vendor Account Options |  |  | Pending
116 | Vendors Plans & Pricings |  |  | Pending
117 | Vendor Current Plan |  |  | Pending
118 | Vendor Create Account |  |  | Pending
119 | Vendor Profile Management |  |  | Pending
120 | Vendor Promotion Page |  |  | Pending
| Total Pages |  | 120
|  | Completed Pages | 1
|  | Pages with minor tweaks | 47
|  | New scope | 1
|  | Awaiting Client Feedback | 15
|  | Pages I have to review | 16
|  | Pending Pages | 40
some changes done